## checkList
| WDD_Project_2025 | Done Y/N? | Team Member
Week | Goals for this week |  | Hande Eda Ozdemir | Htet Oo Khin | Menomi Gamage
week 8
| read brief & be familiar with it | Y
| brainstorm with group - what sustainability goal to use | Y
| team member strengths and weaknesses | Strengths | HTML and JS | HTML | HTML coding and JavaScript
|  | Weaknesses | sometimes CSS | CSS, JS | CSS
| 1 person creates a shared folder and shares it! | Y
| my own wireframe | Y
| sitemap for whole website | Y
week 9
| Research topics related to Sustainability of life below water | Y
| Set up initial HTML pages | Y
| Build a skeleton website (contain all 6 pages) | Y
| Home Page and About page | Y
| Gallery and NASA page | N
| Threats and What can we do page | Y
| Code the navigation bar ( consistant across all pages) | Y
| Set up CSS file | Y
| incoporate responsive elements (desktop/mobile) | Y
| Test Website in various screen sizes | Y
| Screenshots and progress evidence of each webpage | Y
record who contributed - meeting and coding
Let Emer know if someone is out of contact
week 10
| Add content and images etc into skeleton website | Half
| Develop more CSS ?? | Y
| Set up JS file and incoporate elements | Y
| Update GitHub repo | Y
| Comments in HTML, CSS and JS | Y
| Screenshots and progress evidence of each webpage | Half
week 11
| Add proper design CSS and formatting | N
| JS vaildation for form | N
| Finalies HTML files and the content | N
| Test Webpages and carry out debugging | N
| Update GitHub repo | N
| Screenshots and progress evidence of each webpage | N
week 12 | finish up code | N
| deploy website | N
| testing - functional testing, speed test | N
| Write/record report | N
| only one CSS file - if possible more marks | N
| testing menu links work | N
| comments in HTML, CSS and JS | N
| Make sure the author name is on each webpage | N
| everyone has DOM manipulation on their own webpage | N
Submission | SUNDAY |  | 2 |  | 1

## extra
PROJECT REQUIREMENTS | COMPLETEDü
use bootstrap or responsive framework. *you cannot use a theme. | FALSE
use file path structures. *extra marks | FALSE
consistent navigation across all webpages. | FALSE
meta tags on every HTML file to clearly show the author (for individual grading) | FALSE
comments to clearly demonstrate your contribution in shared files such as report and CSS files. | FALSE
for images on your own webpages, include your initials in the file name | FALSE
comments to clearly show your understanding of code | FALSE
on-going regular commits to your own GitHub repo over the duration of the project | FALSE
REPORT. (demonstrate the following in report) | COMPLETEDü
design | FALSE
project management | FALSE
Before and after screenshots of all testing. (Please note that any screenshots of wireframes attached separately will not be graded, but they must be included within the report document.) | FALSE
Link to deployed website. | FALSE
Links to the public GitHub repo for each student with at least 8 commits demonstrating on-going work (cannot be all in the last 2 weeks). | FALSE
If doing a video report, provide the link to the video demonstration in your document. | FALSE